## 8-Day Plan
Day | Project Goals / Requirements | Tolulope | Fowoyemi | Light | Deliverables / Checkpoints
Day 1 | Architecture planning, repo setup, workflow definition | Define system architecture, API contracts, scoring schema, repo structure, setup backend base | Setup GitHub API module, understand commit payload structure, setup backend environment | Setup frontend project, routing, UI layout, dashboard wireframe | Team alignment complete, repo structure ready, branch strategy established
Day 2 | Core backend and frontend scaffolding | Implement rule-based scoring engine skeleton | Fetch commits from GitHub API, pagination support, repo URL parsing | Build input page and dashboard skeleton | Able to input repo URL and retrieve commit data
Day 3 | Commit analysis pipeline development | Implement scoring rules and composite scoring logic | Build backend endpoints and contributor aggregation | Build leaderboard, commit table, and score cards | Rule-based scores visible in frontend
Day 4 | AI integration and semantic analysis | Integrate Azure OpenAI semantic scoring and JSON parsing | Integrate Azure Text Analytics for language detection | Connect frontend to backend APIs and loading states | LLM scoring operational
Day 5 | Data aggregation and analytics | Optimize scoring pipeline, caching, debugging | Contributor normalization and timeline aggregation | Implement charts and timeline visualizations | Leaderboard and timeline fully functional
Day 6 | Special features and UX polish | Implement Hall of Fame/Shame logic and scoring explanations | Improve backend stability and error handling | Build Hall of Fame/Shame UI and improve responsiveness | Project becomes demo-ready visually
Day 7 | Testing, export, and refinement | Integration testing, API cleanup, final debugging | Performance improvements and endpoint cleanup | Implement report export view and UI polish | Stable near-final build completed
Day 8 | Final delivery and presentation preparation | Prepare presentation, architecture explanation, final merge | Assist testing and documentation | Prepare screenshots/demo flow and presentation visuals | Final demo and README completed